## Sheet1
Steps will be highlighted if A and R are not assigned.
| R: | Does the step
| A: | Accountable for the step
| C: | Consulted with before the step
| I: | Informed about the step is completed
Phase | Description | BA | IA | PM | UX Designer | Developer | Dev Lead | Dev/OPS Mgr | QA | Release Manager | Implementation Team | Communications
PROJECT PLANNING & REQUIREMENTS GATHERING
Kick Off and Requirement Gathering | Initiate Project Kick off meeting with Product Owner/Customer based on Request received | A/R | I | I | X | X | X | X | X | X | X | X
| Meeting with the team to discuss the high level project overview | A/R | R | R | R | R | R | R | X | X | X | X
| Meeting with customer to gather requirements for the Project | A/R | R | R | R | R | R | R | X | X | X | X
| Document the requirements in the functional requirements document | A/R | R | R | R | R | R | R | X | X | X | X
Analysis | Feasibility analysis of requirements & converting functional to UX and (or) technical requirements | R | R | R | C | R | A | R | I | X | X | X
| Complete the requirements document & sign off from customer | A/R | I | I | I | I | I | I | X | X | X | X
MONITORING & CONTROL
Monitoring & Control | Create a Project Charter | I | I | A/R | X | X | X | I | X | X | X | X
| Prioritize Requirements (into Iterations if this is a Scrum based project) | R | R | A/R | I | I | R | R | X | X | X | X
| Estimate Project Effort (UX and/or Development effort) | I | I | A | R | R | A/R | A | X | X | X | X
| Create Project Schedule | I | I | A/R | I | X | X | I | X | X | X | X
| Allocate Resources | I | I | A/R | X | X | X | I | X | X | X | X
| Create Project Site for the Project | I | I | A/R | I | I | I | I | I | X | X | X
| Create Communication Plan | I | I | A/R | X | X | X | I | X | X | X | X
PROJECT DISCOVERY
Discovery | Draft wireframe creation based on requirements | I | A/R | I | C | I | I | I | X | X | X | X
| Baseline Analytics Tracking | I | A/R | I | I | I | I | I | X | X | X | X
| Internal Review of wireframe with team | I | A/R | I | I | I | I | I | X | X | X | X
| Present IA recommendations ( wireframe , analytics to customer) | I | A/R | I | I | I | I | I | X | X | X | X
| Make and changes to wireframe based on client feedback | I | A/R | I | I | I | I | I | I | X | X | X
| Customer sign off on wireframe | I | A/R | I | I | I | I | I | X | X | X | X
| Wireframe handoff to UX designer | I | A/R | I | I | I | I | I | X | X | X | X
PROJECT DESIGN
Design | Preliminary design based on wireframe | I | C | I | A/R | C | I | I | X | X | X | X
| Design Review with the team | I | C | I | A/R | C | I | I | X | X | X | X
| Incorporate team feedback in the design review | I | C | I | A/R | C | I | I | X | X | X | X
| Present the Design to customer (1st Design review) | I | C | I | A/R | C | I | I | X | X | X | X
| Incorporate customer feedback in the design | I | C | I | A/R | C | I | I | X | X | X | X
| Present the Design to customer (2nd round of design review) | I | C | I | A/R | I | I | I | X | X | X | X
| Finalize the design based on final round of customer feedback | I | C | I | A/R | C | I | I | X | X | X | X
| Deliver design to customer | I | I | I | A/R | X | X | X | X | X | X | X
| Design Sign off from customer | I | I | I | A/R | I | I | I | X | X | X | X
| Hand over design in terms of .psds to development team | A/R | I | I | A | I | I | I | X | X | X | X
BUILD/CODING
Coding/Build | Complete HTML coding for the project | I | I | I | I | R | A | A | X | X | X | X
| Complete CSS coding for the project | I | I | I | I | R | A | A | X | X | X | X
| Complete JavaScript coding for the project | I | I | I | I | R | A | A | X | X | X | X
| Integrate Code | I | I | I | I | R | A | A | X | X | X | X
| Write Unit Test Scripts | I | I | I | I | R | A | A | X | X | X | X
| Review Code | I | I | I | I | R | A/R | A | X | X | X | X
| Incorporate Review Comments | I | I | I | I | R | A | A | X | X | X | X
| Round 1 Demo to Team (Including Product Owner) | I | I | A | I | R | A | A | X | X | X | X
TESTING
Testing | QA environment set up | I | I | I | X | R | A | A | I | X | X | X
| QA Test by running test scripts | I | I | A | X | I | I | I | A/R | X | X | X
| Bug Fixes | I | I | I | X | R | A | A | X | X | X | X
| UAT bug fixes (UAT to be done by customer) | I | I | I | X | R | A | A | X | X | X | X
PRE-LAUNCH ACTIVITIES
Pre-Launch | Demo 2 - Final Demo post all bug fixes | I | A | A | I | R | R | A/R | I | I | I | I
| Submission of Request to the Change Approval Board | I | I | A | I | R | R | A | X | I | I | X
| Launch Itenary Creation | X | X | X | X | R | R | A | X | I | R | X
| Deployment Checklist Review | X | X | I | X | R | R | A | X | I | I | I
| Release Review Meeting | I | I | A | I | R | R | A/R | I | I | I | I
| Review & Test Communication | A | I | A | X | X | X | I | X | X | X | A/R
| Code Freeze | X | X | X | X | R | A/R | A/R | X | X | X | X
| Release Pending Communication | A | I | A | X | X | X | I | X | X | X | A/R
IMPLEMENTATION | Final Implementation | I | I | I | I | R | A/R | A/R | I | I | R | I
POST LAUNCH ACTIVITIES
Post-Launch Activities | Training | bar: A to A/R
| Release Implemented Communication | A | I | A | X | X | X | I | X | X | X | A/R
| Release Sign off from Customer | A/R | X | I | X | X | X | X | X | X | X | X
| 90 Day warranty Support to Customer | A/R | I | I | X | I | I | I | X | X | X | X
| Project closure | C | C | A/R | C | C | C | C | X | X | X | X

## Sheet2
BA
IA | R
PM | A
Developer | C
Lead Developer | I
Tester | A/R
Release Manager | X
OPS Team
Dev/OPS Manager
Customer
Designer
Trainer

## Sheet3
Project Taks | Project Roles
| Business Analyst | PM | Architect | Developer | Tester | OPS Group